## Sheet1
wp | activity | start_date | end_date
Aim 1. Elucidate the mechanism of tetracycline inactivation | 1.1. Characterize inactivation products of tetracyclines | 1 | 36
Aim 1. Elucidate the mechanism of tetracycline inactivation | 1.2. Co-crystalize tetracycline substrates with enzymes | 1 | 60
Aim 1. Elucidate the mechanism of tetracycline inactivation | 1.3. Trap substrate binding modes | 1 | 24
Aim 1. Elucidate the mechanism of tetracycline inactivation | 1.4. Screen all enzymes against all tetracyclines in vitro | 13 | 48
Aim 1. Elucidate the mechanism of tetracycline inactivation | 1.5. Measure whole cell activity and Michaelis-Menten kinetics | 25 | 60
Aim 2. Understand the evolution of tetracycline inactivation | 2.1. Improve sequence-based prediction of enzymes | 1 | 60
Aim 2. Understand the evolution of tetracycline inactivation | 2.2. Discover novel tetracycline destructases using functional metagenomics | 1 | 60
Aim 2. Understand the evolution of tetracycline inactivation | 2.3. Understand how distal regions optimize tetracycline inactivation | 13 | 60
Aim 2. Understand the evolution of tetracycline inactivation | 2.4. Understand how domain-level changes optimize FMOs | 13 | 60
Aim 2. Understand the evolution of tetracycline inactivation | 2.5. Study how tetracycline inactivation products influence population dynamics | 13 | 60
Aim 3. Develop inhibitors, chemical probes, and diagnostic agents | 3.1. Explore D-ring substitution pattens of ATC inhibitor scaffold | 1 | 60
Aim 3. Develop inhibitors, chemical probes, and diagnostic agents | 3.2. Explore A-ring substitution | 13 | 30
Aim 3. Develop inhibitors, chemical probes, and diagnostic agents | 3.3. Co-crystalize inhibitors with Type 1 and 2 enzymes | 1 | 60
Aim 3. Develop inhibitors, chemical probes, and diagnostic agents | 3.4. Trap inhiitor binding modes | 31 | 54
Aim 3. Develop inhibitors, chemical probes, and diagnostic agents | 3.5. Synthesize chromogenic tetracyclines as diagnostic agents | 1 | 48